## Job variance
Job cost variance worksheet
BuilderBuzz · Example inputs, not market prices or field results
Edit amber cells. Enter 0 for unused costs. Positive cost variance means an overrun.
Cost category | Estimate ($) | Actual ($) | Variance ($) | Reason / next estimating change
Materials | 12000 | 13200 | 1200 | Quantity and unit-price changes
Burdened labor | 8500 | 9800 | 1300 | Hours and loaded rate
Equipment | 1500 | 1700 | 200 | Rental duration / charges
Allocated overhead | 3000 | 3000 | 0 | Use a consistent allocation method
Subcontractors | 0 | 0 | 0 | Avoid double-counting labor
Other job costs | 0 | 200 | 200 | Include every applicable job cost
Total entered costs | 25000 | 27900 | 2900
Revenue / result | Original plan ($) | Final / current ($) | Change ($) | Definition
Original contract | 32000 | 32000 |  | Excludes sales tax collected for remittance
Approved scope changes | 0 | 1800 |  | Entered changes only; approval is not payment
Modeled revenue | 32000 | 33800 | 1800 | Contract plus entered approved changes
Modeled job profit | 7000 | 5900 | -1100 | Revenue minus ALL entered costs
Modeled margin | 21.88% | 17.46% |  | Profit / revenue; blank when revenue is zero
Change in modeled profit |  | -1100 |  | Revenue change less cost overrun
Synthetic remodel: $2,900 cost overrun, $1,800 approved revenue change, $1,100 less modeled profit.
A live job needs forecast-to-complete costs. Paid-to-date spending alone understates the eventual cost.
Modeled job profit is not company net income or cash collected. Missing costs change the result.
Method: compare the estimate with actual cost using the same scope and cost categories.
Source: https://www.gao.gov/products/gao-20-195g
Guide: https://builderbuzz.com/job-costing-calculator